## Test Plan Template
Test Plan Template
Test Plan Identifier: |  |  | SL-TP-2025-001
Introduction: |  |  | This test plan document outlines the comprehensive testing strategy for the Sauce Demo e-commerce platform. The testing will cover both functional and non-functional requirements to ensure optimal user experience across all supported devices and browsers.
Objectives: |  |  | This test plan outlines the comprehensive testing approach for the Sauce Demo e-commerce platform to ensure that all core functionalities work correctly across web and mobile platforms.
Test Scope: |  |  | Web application, login module, cart functionality, product catalog, checkout process.
Date: 17/06/25
Start date - 15/05/25
Test Items+A11:L15D8A11:M16A11:N17D8A11:M16A11:O17D8A11:M16A11:O19A11:O18A11:Q16A11:PA11:O14 | Features to be Tested | Features Not to be Tested | Test Environment & Tools | Resources | Test Types | Test Strategy and Approach | Entry Criteria | Exit Criteria | Deliverables | Start Date | End Date | Assigned to | Risks and Contingencies | Notes
User Login & Authentication | Login using valid credentials | Admin login, session timeout | Chrome browser, Selenium WebDriver | 1 QA tester, login credentials | Functional, Security | Black-box testing, basic authentication flow testing | Swag Labs website loads and login form is visible | Redirected to inventory page after successful login | Test case logs, browser screenshots | 20/6/2025 | 2025-06-21 | QA Team | Login button not clickable, backend authentication service fails | Ensure login button works, verify that URL contains inventory after login
Add to Cart | Add product to cart, verify cart badge count | Removing items, adding multiple items | Chrome browser, Selenium WebDriver | 1 QA tester | Functional | Black-box UI interaction test | User successfully logged in, product list is visible | Cart badge displays correct quantity | Test logs, screenshots of cart | 2024-06-21 | 2025-06-22 | QA Team | Button ID changes, cart badge not updating | Test “Add to Cart” button and validate badge shows correct quantity
Shopping Cart & Checkout | Add item to cart, open cart, fill checkout form, complete purchase | Inventory sync, tax, shipping cost logic | Chrome browser, Selenium WebDriver | Test payment cards, multiple user accounts, order management system | Functional, Integration, Performance | End-to-end flow testing, form validation, final confirmation page check | User logged in, item added to cart | “Thank you” confirmation message is displayed | Checkout test logs, screenshots of confirmation page | 22/6/2025 | 2025-06-24 | QA Team | Element not found due to DOM change, checkout flow changes | Full flow: add product → go to cart → checkout → confirm order
Product Filter | Change product sorting to “Name (Z to A)” | Other sorting methods, backend product data | Chrome browser, Selenium WebDriver | 1 QA tester | Functional | UI dropdown interaction, sorting logic test | User logged in, sort dropdown is visible | Product list is sorted alphabetically in reverse order | Screenshots, logs showing selected filter option | 24/6/2025 | 2025-06-25 | QA Team | Filter option label changed, dropdown interaction fails | Verify dropdown functionality and ensure sorting works correctly (Z to A)
Test Plan Team | [12 empty] | Related Free Templates
Name |  |  | Role |  | Responsibilities
Joe Dohn |  |  | QA Team |  | Test coordination across all features (User Login, Add to Cart, Shopping Cart, Checkout, Product Filter), overall test planning and reporting | [7 empty] | Gantt Chart Template
John Doe |  |  | QA Team |  | Security testing focusing on User Login and Checkout processes, penetration testing, vulnerability assessment | [7 empty] | Dashboard Template
Watcharaporn Pakornmaneekul |  |  | QA Team |  | Load and stress testing for Shopping Cart, Add to Cart, and Checkout features; performance optimization | [7 empty] | Task Tracker Template
Rujiphas Pakornmaneekul |  |  | QA Team |  | Mobile testing for all features including User Login, Add to Cart, Shopping Cart, Checkout, and Product Filter — device compatibility and mobile UX